## Overview
Project Name
Unified Data Integration System | Unified Data Integration System (UDIS) - Project Management Plan
| Project Description | Key Stakeholders
| A centralized data management system to automate data integration from multiple sources. | Stakeholders list here...

## Objectives
Objective | Description
Improve data accessibility | Create a centralized data repository.
Automate data retrieval | Reduce manual processes through automation.
Ensure data accuracy | Implement validation mechanisms to maintain data integrity.
Facilitate collaboration | Provide a single source of truth for all team members.

## Data Sources
Source Name | Description
TM1 | Data source for actuals.
Global Headcount File | Source for headcount data.
Taleo | Recruitment data source.
Anaplan | Planning and budgeting data.
Appian | Workflow management system.
Ledger | Financial data source.
COO/BMs | Input from Chief Operating Officers and Business Managers.
Hiring Manager | Data related to hiring.
Leads | Data related to prospective candidates.
Position Tracker | Current positions and statuses.
Inputs by HR | Human Resource input data.

## File Structure
File Name | Description | Content
Headcount GHA File | Base file containing PID, open positions, and physical roles. | Data from January to December with adjustments for moves and exits.
TM1 Actuals | Contains actual data for analysis. | Monthly data reflecting performance.
Adjustment Requests | File to accommodate any change requests. | Monthly updates reflecting modifications.

## Challenges
Challenge | Impact | Resolution
Heavy file sizes | Slow processing | Optimize data handling and storage.
Tracking changes | Inaccurate data | Implement a change log.
Acceptance issues | Lack of understanding | Conduct training sessions for COOs.
Scattered information | Inefficiency | Centralize data access.
Parallel conversations | Wasted time | Standardize communication protocols.
Consistent knowledge | Inconsistency | Develop a knowledge base.
Inconsistent practices | Varying data quality | Standardize processes.
Level loading | Uneven workload | Implement a balanced workload strategy.
Ways of working | Collaboration issues | Define clear workflows.

## Implementation Plan
Phase | Task | Responsible | Timeline
Phase 1 | Requirement gathering | Team | Q1 2024
Phase 2 | System development | Developers | Q2 2024
Phase 3 | Testing | QA Team | Q3 2024
Phase 4 | Training | HR | Q4 2024
Phase 5 | Deployment | IT | Q1 2025

## Sheet1
Key Activities | Data Sources | Automation Opportunities | Benefits | Phase | Current Effort | Remarks
Data Collection | TM1, Taleo, Anaplan, Appian, Global Headcount, etc. | Automate data extraction using Python or APIs to pull data from source systems. | Reduces manual effort and errors; faster data collection. | Phase 1: Data Gathering | High | Need to coordinate with BMs to gather data and understand current processes.
Identify Data Sources | Business Managers (BMs) | Create automated scripts or macros to gather data directly from BMs’ databases. | Streamlines communication and ensures consistent data sourcing. | Phase 1: Data Gathering | High | Ensure alternative data sources are available if direct access isn’t possible.
Data Consolidation | Excel, CSV, SQL databases | Automate merging of data from multiple files into a master file. | Saves time, increases accuracy in data consolidation. | Phase 2: Automation Development | Medium | Use Python's pandas or Excel macros to integrate data sources efficiently.
Validate and Track Data | TM1, Taleo, Headcount files | Use validation scripts to ensure accuracy in collected data. | Reduces errors and inconsistencies. | Phase 3: Testing & Validation | Medium | Rule-based validation will need stakeholder input.
Provide Reports to COOs | COO-tailored reports based on integrated data | Automate report generation with dashboards and customized views for COOs. | Ensures consistent format and data across all reports. | Phase 4: Reporting | Low | Focus on making reports dynamic and relevant to each COO’s needs.
Adjustments & Reconciliation | Adjustment requests from teams | Automate tracking and reconciliation of adjustment requests via an adjustment file. | Ensures all adjustments are reflected in final reports. | Phase 3: Testing & Validation | Medium | Need clear protocols on how and when adjustments are made.
Additional Notes:
Data Sources Identification: Work with the BMs to identify primary data sources and any potential backups. Once sources are confirmed, automate the extraction process.
Automation Development: Focus initially on data extraction and validation; then move to reporting automation.
Current Challenges: High effort currently required for manual data collection and tracking, but automation will reduce this significantly.
This table focuses on streamlining data collection and identifies automation opportunities to help reduce manual work and increase accuracy. Would you like to include any specific tools or technologies in this table?