## Slide 1: Monthly Update – Automation Projects
Executive Summary
Progress continues on automation initiatives across Anaplan, GSC Recharges, and Global Role data. Phase 1 of GSC Recharges has been delivered. Updates for new structural changes (L3/L4) and evolving input requirements are underway.
Key Achievements (Last Period)
- Delivered Anaplan split reports - Sent GSC Recharges tool to SPOCs (Phase 1) - Global Role initial data structured - Delivered GIRS file (awaiting updates) - Started updates for L3/L4 structure
Planned Activities (Next Period)
- GSC Recharges Phase 2 billing validation - GIRS file rework post updated input - Appian + hiring file automation (20-May-2025) - Finalize Anaplan automation (23-Apr-2025) - Continue Global Role iterations
Management Attention / Key Risks
- GIRS input pending from owner - GSC Recharges Phase 2 reliant on SPOC input - L3/L4 structural changes impacting existing tools
New Requests / Additions
- Global Role & Anaplan enhancements requested - Hiring automation added (Appian + validations)