## Sheet1
Phase | Key Activities | Automation Opportunities | Benefits | Remarks | Automation Status | Timeline
Phase 1: Initial Approach | Built logic for identifying new and changed records; Created workflows for data integration and validation; Tested solution with sample data. | Limited automation due to scalability challenges in the initial logic. | Preliminary workflows established; Foundation for future iterations. | Challenges with merging and blank rows; Decision to pivot to a new approach. | Partially Automated | Completed
Phase 2: New Approach | Rebuilt logic for appending data; Resolved issues with blank rows and duplicates; Implemented modular code design. | Improved handling of dynamic updates; Streamlined merge logic for automation. | Improved reliability, scalability, and modularity; Resolved inconsistencies in data handling. | Resolved core issues; Focused on scalability and dynamic handling. | Partially Automated | In Progress
Phase 3: Next Steps | Perform lookups for GHA and Open Position records; Automate updates; Validate and test the final master file. | Reusable functions for data updates and appending; Final validation process automation. | Streamlined updates; Ensures accurate and consistent master file creation. | Final step before deployment; Awaiting feedback from stakeholders. | To be Automated | Upcoming